## Project Planning Template
Bright learn Coffee Case Study 2026: Project Planning Gantt Chart
Start Date: 30 July 2026 | Submission Date: 07 August 2026
Task Phase | Task Description | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Planning & Architecture | 1. Design data flow diagram (Miro) | bar: Day 1 to Day 3
2. Define key insights & calculations | bar: Day 1 to Day 2
Data Processing | 1. Convert Excel to CSV | bar: Day 1
2. Load CSV into Databricks | bar: Day 1
3. Clean & transform data (unit_price, buckets) | bar: Day 1 to Day 3
4. Compute totals & aggregations | bar: Day 1 to Day 2
Data Analysis | 1. Export processed data to Excel/Power BI | bar: Day 1
2. Build dashboards (pivot tables, charts) | bar: Day 1 to Day 5
Presentation | 1. Draft methodology document | bar: Day 1 to Day 2
2. Prepare CEO presentation (PowerPoint/Canva) | bar: Day 1 to Day 3
3. Final review & submission | bar: Day 1 to Day 2